## Participants
Inspection Roles
No | Group Member | Roles | Comment
1 | Nguyen Thi Dung Nhi | Author | Checking User Interface Design document
2 | Pham Anh Khoa | Inspector, Recorder | Checking Project Plan document
3 | Nguyen Van Huong | Inspector | Checking Test case document
4 | Nguyen Phuc Hung | Inspector | Checking Software Requirement Specification document
5 | Nguyen Nho Quoc Huy | Inspector | Checking Defined process document

## Schedules
Inspection Schedule
No | Task | Task owner | Start time | End time | Comment
1 | Nguyen Thi Dung Nhi | Checking User Interface Design document | 2024-01-27 | 2024-01-27
2 | Pham Anh Khoa | Checking Project Plan document | 2024-01-27 | 2024-01-27
3 | Nguyen Van Huong | Checking Code, Test case document | 2024-01-29 | 2024-01-29
4 | Nguyen Phuc Hung | Checking Software Requirement Specification document | 2024-01-29 | 2024-01-30
5 | Nguyen Nho Quoc Huy | Checking Defined process document | 2024-01-27 | 2024-01-27

## Materials
Inspection Material
No | Group Member | Tool/Material | Quantity | Comment | Approval
1 | Nguyễn Văn Hướng | Apache NetBeans, Excel, Word | All Documents | Responsible for checking Code and Test Case document | x
2 | Nguyễn Phúc Hưng | Excel, Word | All Documents | Responsible for checking Software Requirement document | x
3 | Nguyễn Nho Quốc Huy | Excel, Word | All Documents | Responsible for checking Defined Process document | x
4 | Phạm Anh Khoa | Excel, Word | All Documents | Responsible for checking Project Plan document | x
5 | Nguyễn Thị Dung Nhi | Excel, Word | All Documents | Responsible for checking User Interface Design document | x